## Slide 1: PROBLEMS

## Slide 2: Problem 1
Given,
Optimistic LOC, Sopt = 2600
Pessimistic LOC,Spess = 4000
Most Likely LOC, Sm= 3800
Calculate the expected value for the estimation variable

## Slide 3: Problem 1 Solution
The expected value of the estimation variable,
S = (Sopt + 4* Sm + Spess) /6
= (2600+ 4* 3800 + 4000)/6
S = 3633

## Slide 4: Problem 2
Given
The estimated LOC count is 56,100
From the review of historical data, below two values were derived
  Average productivity for this category of systems = 693 LOC/pm
  Burdened labor rate = $8000/month
  Compute the below,
  Cost per LOC
  Total Estimated Project Cost
  Estimated Effort in person months

## Slide 5: Problem 2 Solution
Cost per LOC = Labor rate per month/LOC per pm
= 8000/693 = $11.5
Total Estimated Project Cost = Estimated LOC * Cost per LOC
= 56,100 * 11.5 = $6,45,150
Estimated Effort in pm = Total Estimated Project Cost/ Labor rate per month
= 6,45,150/8000 = 81 person months

## Slide 6: Function Points

## Slide 7: Problem 3
Information Domain Value Count | Opt | Likely | Pess | Estimated Count | Weight Average | FP Count
Inputs | 20 | 24 | 34 | ? | 4 | ?
Outputs | 12 | 17 | 22 | ? | 5 | ?
Inquiries | 16 | 26 | 33 | ? | 5 | ?
Files | 4 | 5 | 7 | ? | 10 | ?
Interfaces | 2 | 4 | 6 | ? | 7 | ?
Count Total |  |  |  |  |  | 
Given the above table, with default simple weight for all categories and the Complexity Factor = 1.19.
compute
The estimated count for each value
Total Unadjusted FP
Adjusted FP Count

## Slide 8: Problem 3 - Contd
Also, if the below historical data are given,
Organizational Average Productivity of this type of system = 5.8 FP/m
Burdened Labor Rate = $8000/m
Compute
Cost per FP
Total Estimated Project Cost
Estimated Effort in person months

## Slide 9: Problem 3 - Solution
Information Domain Value Count | Opt | Likely | Pess | Estimated Count | Weight | FP Count
Inputs | 20 | 24 | 34 | 24 | 4 | 96
Outputs | 12 | 17 | 22 | 17 | 5 | 85
Inquiries | 16 | 26 | 33 | 26 | 5 | 130
Files | 4 | 5 | 7 | 5 | 10 | 50
Interfaces | 2 | 4 | 6 | 4 | 7 | 28
Count Total |  |  |  |  |  | 389
UFP(Unadjusted FP) = 389
VAF(value adjustment factors) = 0.65 + 0.01 * ∑Fi = 0.65 + 0.01 * 1.19 = 0.66
AFP(Adjusted FP Count) = UFP * VAF = 389 * 0.66 = 257

## Slide 10: Problem 3 – Solution Contd
Cost per FP = Labor rate per month/FP per month
= 8000/5.8 = $1379
Total Estimated Project Cost = AFP * Cost per FP = 257 * 1379 = $ 3,54,403
Estimated Effort in person months = Total Estimated Project Cost/Labor rate per month = 3,54,403/8000 = 44 pm

## Slide 11: Problem 4
For the given data, compute the effort in person months using the COCOMO model
Objects’ Count
Objects’ Complexity Weight
Object Type | Count of each object |  | 
 | Simple | Medium | Difficult
Screen | 5 | 4 | 5
Report | 6 | 7 | 5
3GL Comp |  |  | 6
Object Type | Complexity Weight |  | 
 | Simple | Medium | Difficult
Screen | 1 | 2 | 3
Report | 2 | 5 | 8
3GL Comp |  |  | 10
Also given,
Percentage of reuse is 30%,
Value of PROD = 7
Compute the effort in person months.

## Slide 12: Problem 4 - Solution
Object Type | Object Points Calculation |  |  | Count
 | Simple | Medium | Difficult | 
Screen | 5 * 1 | 4 * 2 | 5 * 3 | 28
Report | 6 * 2 | 7 * 5 | 5 * 8 | 87
3GL Comp |  |  | 6 * 10 | 60
Object Points Count = 28 + 87 + 60 = 175
NOP = Object Points * [(100 - % reuse)/100] = 175 * 70/100 = 122.5
Estimated Effort = NOP/PROD = 122.5/7 (LOW) = 17.5 pm

## Slide 13: Problem 5
Given,
Probability of occurrence of a risk, P = 0.5
Cost to the project if the risk occurs,
C = $ 20, 600
Calculate Risk Exposure

## Slide 14: Problem 5 - Solution
Risk Exposure = P * C
= 0.5 * 20, 600
= $10, 300

## Slide 15: Problem 6
Using the simplified Software Equation Model, compute the effort in person months, given the below data,
Estimated LOC = 33580
Productivity Parameter, P = 12,000
Special Skills Factor ,B = 0.28

## Slide 16: Problem 6 Solution
Simplified Software Equation Estimation Model
tmin = 8.14 (LOC/P)0.43
E = 180*B*t3
Substituting,
tmin = 8.14 (33580/12000)0.43 = 8.14 *(2.8)0.43 =8.14 * 1.6 = 13 pm = 1.08 person years
E = 180 * 0.28 * (1.08)3 = 63.5 pm

## Slide 17
Problem 7

## Slide 18: Problem 7 - Solution
Expected Cost = ∑ (Path Probabilityi * Estimated Path Costi)
Expected Costbuild = 1, 40, 000 + 2, 70, 000
= $ 4, 10, 000
Expected Costreuse = 78000 + 0.70 [0.20 * 3,17,000 + 0.80 * 4, 96,000] = $ 4, 00, 140
Expected Costbuy = 1, 38, 450 + 1, 41, 750 = $ 2, 80, 200
Expected Costcontract = 70600 + 329600 = $ 4, 00, 200
The decision would be to buy the software.
Notes: Reuse Sub tree = 3,22,140

## Slide 19: Problem 8
Adaptation Criteria | Grade | Weight | New Dev – Entry Point Multiplier
Size | 2 | 1.2 | 1
No of Users | 3 | 1.1 | 1
Business Criticality | 4 | 1.1 | 1
Longevity | 3 | 0.9 | 1
Req. Stability | 4 | 1.2 | 1
Ease of Communication | 2 | 0.9 | 1
Maturity of Tech | 2 | 0.9 | 1
Perf Constraints | 3 | 0.8 | 1
Embedded/Non Emb. | 3 | 1.2 | 1
Project Staffing | 1 | 1.0 | 1
Interoperability | 3 | 1.1 | 1
Engg. Factors | 0 | 1.2 | 0
Given, the below adaptation criteria, graded for a new dev project, with low risk, Calculate TSS and conclude on the degree of rigor that you choose for applying process.

## Slide 20: Problem 8 - Solution
Adaptation Criteria | Grade | Weight | New Dev – Entry Point Multiplier | TTS
Size | 2 | 1.2 | 1 | 2.4
No of Users | 3 | 1.1 | 1 | 3.3
Business Criticality | 4 | 1.1 | 1 | 4.4
Longevity | 3 | 0.9 | 1 | 2.7
Req. Stability | 4 | 1.2 | 1 | 4.8
Ease of Communication | 2 | 0.9 | 1 | 1.8
Maturity of Tech | 2 | 0.9 | 1 | 1.8
Perf Constraints | 3 | 0.8 | 1 | 2.4
Embedded/Non Emb. | 3 | 1.2 | 1 | 3.6
Project Staffing | 1 | 1.0 | 1 | 1
Interoperability | 3 | 1.1 | 1 | 3.3
Engg. Factors | 0 | 1.2 | 0 | 0
Average TSS = 2.7
TSS < 1.24 – Casual
TSS between 1 and 3 – Structured
TSS > 2.4 - Strict
So structured, application is chosen
Notes: TSS < 1.24 – Casual
TSS between 1 and 3 – Structured
TSS . 2.4

## Slide 21: Problem 9
Task ID | Planned Effort | Actual Effort | Scheduled Cost | Actual Cost
1 | 17 | 18 | 1700 | 1800
2 | 10 | 12 | 1000 | 1200
3 | 15 | 13 | 1500 | 1300
4 | 16 | 19 | 1600 | 1900
5 | 11 | - | 1100 | -
6 | 9 | - | 900 | -
.. | … | .. | .. | ..
.. | … | .. | .. | ..
Given, the above project table, while you are asked to perform the EVA, 6 tasks should have been completed as per schedule. But only 4 tasks have bee completed. Calculate Scheduled Performance Index (SPI), ScheduledVariance (SV), Percent scheduled for complete, Percent Complete, Cost Perfprmance Index(CPI), Cost Variance(CV), Total budget is $15, 000

## Slide 22: Problem 9 - Solution
budgeted cost of work scheduled(BCWS) = $ 7800
budgeted cost of work performed(BCWP )= $ 5800
Actual cost of work performed(ACWP) = $ 6200
Scheduled performance index(SPI) = BCWP/BCWS
= 5800/7800 = 0.75
Scheduled Variance (SV) = BCWP – BCWS
= 5800 – 7800 = -2000
Percent Scheduled = BCWS/BAC = 52%
Percent Complete = BCWP/BAC = 39%
CPI = BCWP/ACWP = 0.93
CV = BCWP – ACWP = -400